## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a researcher, I want to define the product domain so that the platform can generate research personas for the correct product context. | MUST HAVE | None | Tanusri | Done
Sprint 1 | Sprint 1 | US-02 | As a researcher, I want to enter the product description, target audience, and research objective so that persona generation is grounded in the study context. | MUST HAVE | US-01 | Tanusri | Done
Sprint 1 | Sprint 1 | US-03 | As a researcher, I want to generate a chosen number of synthetic personas so that I can create a scalable research sample without using real user data. | MUST HAVE | US-02 | Tanusri | Done
Sprint 1 | Sprint 1 | US-04 | As a researcher, I want to type the persona count directly or use the up/down controls so that I can quickly choose the required sample size. | SHOULD HAVE | US-03 | Tanusri | Done
Sprint 1 | Sprint 1 | US-05 | As a researcher, I want persona generation to use Llama 3.2 through Ollama so that the platform can run the generation locally. | MUST HAVE | US-03 | Tanusri | Done
Sprint 1 | Sprint 1 | US-06 | As a researcher, I want personas generated in batches so that larger persona sets can be produced efficiently. | MUST HAVE | US-05 | Tanusri | Done
Sprint 1 | Sprint 1 | US-07 | As a researcher, I want generated personas to be validated for required fields and uniqueness so that the research sample is usable. | MUST HAVE | US-06 | Tanusri | Done
Sprint 1 | Sprint 1 | US-08 | As a researcher, I want to view generated persona profiles clearly so that I can review the synthetic participants before research activities. | MUST HAVE | US-07 | Tanusri | Done
Sprint 2 | Sprint 2 | US-09 | As a researcher, I want to enter survey questions so that each synthetic persona can provide a response. | MUST HAVE | US-08 | Tanusri | Done
Sprint 2 | Sprint 2 | US-10 | As a researcher, I want previous survey questions to appear as searchable suggestions after focusing the question box so that I can reuse earlier questions without auto-filling them. | SHOULD HAVE | US-09 | Tanusri | Done
Sprint 2 | Sprint 2 | US-11 | As a researcher, I want personas to answer survey questions using their generated context so that responses reflect the intended synthetic users. | MUST HAVE | US-09 | Tanusri | Done
Sprint 2 | Sprint 2 | US-12 | As a researcher, I want each generated response classified as positive, neutral, or negative from its actual content so that sentiment analytics reflect the research evidence. | MUST HAVE | US-11 | Tanusri | Done
Sprint 2 | Sprint 2 | US-13 | As a researcher, I want survey responses organized by research scenarios so that I can compare evidence across different research themes. | MUST HAVE | US-11 | Tanusri | Done
Sprint 2 | Sprint 2 | US-14 | As a researcher, I want Interview Mode to generate persona-specific interview responses so that I can explore deeper qualitative feedback. | MUST HAVE | US-08 | Tanusri | Done
Sprint 2 | Sprint 2 | US-15 | As a researcher, I want Insights and Scoring in Interview Mode so that interview findings can be reviewed without leaving the interview workflow. | SHOULD HAVE | US-14 | Tanusri | Done
Sprint 3 | Sprint 3 | US-16 | As a researcher, I want Insight Analytics to calculate positive, negative, and neutral response counts from actual generated responses so that the metrics are evidence-based. | MUST HAVE | US-12 | Tanusri | Done
Sprint 3 | Sprint 3 | US-17 | As a researcher, I want Insight Quality Validation scores to change according to evidence coverage, theme relevance, and persona consistency so that the score reflects the available research evidence. | MUST HAVE | US-13 | Tanusri | Done
Sprint 3 | Sprint 3 | US-18 | As a researcher, I want insights across scenarios so that common patterns and differences can be identified across the research. | MUST HAVE | US-16 | Tanusri | Done
Sprint 3 | Sprint 3 | US-19 | As a researcher, I want the platform to show whether personas would use the product so that adoption intent can be summarized across the sample. | SHOULD HAVE | US-16 | Tanusri | Done
Sprint 3 | Sprint 3 | US-20 | As a researcher, I want a Research Report generated from the insight analytics so that the project findings can be shared as a consolidated output. | MUST HAVE | US-17, US-18 | Tanusri | Done
Sprint 3 | Sprint 3 | US-21 | As a researcher, I want the final report to contain sentiment percentages and circular charts so that the distribution of responses is easy to understand. | SHOULD HAVE | US-16, US-20 | Tanusri | Done
Sprint 3 | Sprint 3 | US-22 | As a researcher, I want the PDF report to preserve charts, clusters, circular shapes, and continuous text without unwanted square artifacts or page gaps. | MUST HAVE | US-20 | Tanusri | Done
Sprint 3 | Sprint 3 | US-23 | As a researcher, I want an overall conclusion on the final report page so that the main research outcome is summarized clearly. | SHOULD HAVE | US-20 | Tanusri | Done
Sprint 3 | Sprint 3 | US-24 | As a researcher, I want the application to handle large persona generation and LLM errors gracefully so that generation can continue or report useful failures. | MUST HAVE | US-06 | Tanusri | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 158 | 60 | 60 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG - Synthetic User Generation Platform
US-01 | T-01 | Build product domain selector with predefined domains and Others option | 2026-07-28 | 2026-08-05 | Tanusri | Design Console | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Add product description, target audience, and research objective inputs | 2026-07-28 | 2026-08-05 | Tanusri | Design Console | Done | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Implement synthetic persona schema and generation endpoint | 2026-07-28 | 2026-08-05 | Tanusri | Persona Generation | Done | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-04 | Add direct persona-count input with increment/decrement controls | 2026-07-28 | 2026-08-05 | Tanusri | Persona Generation | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-05 | Connect backend persona generation to Gorq, Cerebras, Gemini | 2026-07-28 | 2026-08-05 | Tanusri | LLM Integration | Done | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-06 | Implement persona batch generation and response aggregation | 2026-07-28 | 2026-08-05 | Tanusri | Batch Processing | Done | 8 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-07 | Validate persona JSON, required fields, and duplicate profiles | 2026-08-13 | 2026-08-21 | Tanusri | Validation | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-08 | Render generated persona cards and research-ready persona details | 2026-08-13 | 2026-08-21 | Tanusri | Persona UI | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-09 | Implement Survey Mode question input and response request flow | 2026-08-13 | 2026-08-21 | Tanusri | Survey Mode | Done | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-10 | Add focus-triggered previous-question history suggestions and clear action | 2026-08-13 | 2026-08-21 | Tanusri | Survey Mode | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-11 | Generate persona-specific survey responses from persona context | 2026-08-13 | 2026-08-21 | Tanusri | Survey Generation | Done | 10 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-12 | Classify actual survey responses into positive, neutral, or negative sentiment | 2026-08-13 | 2026-08-21 | Tanusri | Sentiment Analysis | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-13 | Organize survey evidence by research scenarios | 2026-08-31 | 2026-09-09 | Tanusri | Scenario Analysis | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-14 | Implement Interview Mode response generation | 2026-08-31 | 2026-09-09 | Tanusri | Interview Mode | Done | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-15 | Add Interview Mode Insights and Scoring actions | 2026-08-31 | 2026-09-09 | Tanusri | Interview Mode | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-16 | Calculate evidence-based positive, neutral, and negative counts | 2026-08-31 | 2026-09-09 | Tanusri | Insight Analytics | Done | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-17 | Implement dynamic Insight Quality Validation metrics | 2026-08-31 | 2026-09-09 | Tanusri | Quality Validation | Done | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-18 | Generate cross-scenario insights from supplied research evidence | 2026-08-31 | 2026-09-09 | Tanusri | Insight Analytics | Done | 10 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-19 | Aggregate Would Use Product intent across personas | 2026-09-14 | 2026-09-17 | Tanusri | Adoption Analysis | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-20 | Generate Research Report from Insight Analytics output | 2026-09-14 | 2026-09-17 | Tanusri | Research Report | Done | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T-21 | Render sentiment percentages and circular charts in report output | 2026-09-14 | 2026-09-17 | Tanusri | Research Report | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-22 | Fix PDF text flow, page gaps, and unwanted square artifacts while preserving graphics | 2026-09-14 | 2026-09-17 | Tanusri | PDF Generation | Done | 8 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-23 | Add overall conclusion to the final report page | 2026-09-14 | 2026-09-17 | Tanusri | PDF Generation | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T-24 | Add LLM retry and error handling for large persona generation | 2026-09-14 | 2026-09-17 | Tanusri | Reliability | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Date | Impediments | Action Taken
Sprint 1 | 2026-07-28 | Mentor explained that the product-domain, product description, target audience, and research objective should be clearly defined before persona generation so the generated users stay relevant to the research context. | I finalized the Design Console inputs and tested the product-domain and research-information flow.
Sprint 1 | 2026-07-30 | Mentor explained that the persona count should be easy to enter and should support both direct typing and the existing increment/decrement controls. | I added and tested direct persona-count entry while keeping the up/down controls.
Sprint 1 | 2026-08-03 | Mentor explained that the synthetic personas should be generated from the research inputs and should not depend on hard-coded persona data. | I connected persona generation to the supplied research inputs and kept the persona records synthetically generated.
Sprint 1 | 2026-08-05 | Mentor explained that the LLM output must follow a consistent structure so that every generated persona can be processed by the platform. | I implemented structured persona output, batch generation, validation, and error handling for the generation flow.
Sprint 2 | 2026-08-13 | Mentor explained that previous survey questions should be available as suggestions only when the question field is selected, rather than automatically filling the field. | I implemented the focus-based question history suggestions and clear behavior without changing the existing input design.
Sprint 2 | 2026-08-17 | Mentor explained that every survey response should be grounded in the corresponding persona instead of giving generic answers. | I updated the response-generation flow to pass the relevant persona context with each question.
Sprint 2 | 2026-08-19 | Mentor explained that positive, neutral, and negative sentiment should be calculated from the actual generated responses instead of using fixed values. | I updated sentiment handling so the categories are derived from the generated response content.
Sprint 2 | 2026-08-21 | Mentor explained that Interview Mode should provide its own insights and scoring without taking the user away from the interview workflow. | I added the Insights and Scoring actions inside Interview Mode and connected them to the analytics output.
Sprint 3 | 2026-08-31 | Mentor explained that Insight Analytics percentages and counts must change according to the actual generated research evidence. | I changed the analytics aggregation to calculate counts and percentages from the available responses.
Sprint 3 | 2026-09-02 | Mentor explained that Insight Quality Validation should not return the same score for different evidence sets. | I updated validation so the score is calculated from evidence coverage, theme relevance, and persona consistency.
Sprint 3 | 2026-09-07 | Mentor explained that cross-scenario insights should be based on the responses available for each research scenario. | I updated the scenario-level aggregation and insight extraction to use the supplied response evidence.
Sprint 3 | 2026-09-09 | Mentor explained that the Would Use Product analysis should represent the generated persona responses rather than a fixed or repeated percentage. | I updated the adoption-intent aggregation and display to reflect the generated persona evidence.
Sprint 3 | 2026-09-14 | Mentor explained that the Research Report action should be positioned after the Insight Analytics and validation information so the workflow is clear. | I positioned the Research Report action below the relevant Insight Analytics sections.
Sprint 3 | 2026-09-15 | Mentor explained that the PDF should retain the existing graphs and visual elements while removing unwanted text-rendering artifacts and page gaps. | I adjusted the PDF text rendering and page flow while preserving the existing charts and graphical elements.
Sprint 3 | 2026-09-16 | Mentor explained that the final research report should contain an overall conclusion summarizing the generated research findings. | I added the overall conclusion to the final page of the Research Report.
Sprint 3 | 2026-09-17 | Mentor explained that local LLM generation should handle temporary failures safely so persona generation does not stop unnecessarily. | I connected the backend to Gorq, Cerebras, Gemini and added retry and error handling for the local LLM generation flow.

## Retrospection
| Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-28 | 2026-08-05 | Tanusri | Start defining the research context before implementation. | Stop changing unrelated UI while connecting the backend. | Continue keeping the product inputs clear and consistent. | I finalized the Design Console inputs and verified the product-domain and research-information flow.
2 | Sprint 1 | 2026-07-28 | 2026-08-05 | Tanusri | Start validating the persona-count flow with different values. | Stop relying only on fixed persona-count controls. | Continue keeping the existing UI behavior unchanged where it is not part of the requested feature. | I added and tested direct persona-count entry together with the increment/decrement controls.
3 | Sprint 1 | 2026-07-28 | 2026-08-05 | Tanusri | Start testing persona generation against the complete research context. | Stop using any hard-coded persona information. | Continue generating personas synthetically from the supplied research inputs. | I connected persona generation to the supplied research inputs and verified synthetic persona creation.
4 | Sprint 1 | 2026-07-28 | 2026-08-05 | Tanusri | Start validating large persona batches and structured output. | Stop accepting malformed or incomplete LLM output. | Continue validating required persona fields and handling generation errors. | I implemented structured persona output, batch generation, validation, and error handling.
5 | Sprint 2 | 2026-08-13 | 2026-08-21 | Tanusri | Start testing question history with different survey questions. | Stop auto-populating a previous question when the question field is not focused. | Continue keeping question history easy to access without changing the existing input design. | I implemented focus-triggered previous-question suggestions and the clear behavior.
6 | Sprint 2 | 2026-08-13 | 2026-08-21 | Tanusri | Start checking responses against each persona before using them for analysis. | Stop using generic responses that do not reflect the persona context. | Continue grounding every response in the generated persona profile. | I updated response generation to use the relevant persona context for each survey question.
7 | Sprint 2 | 2026-08-13 | 2026-08-21 | Tanusri | Start checking sentiment from the complete generated response text. | Stop using fixed positive, neutral, or negative values. | Continue deriving analytics from actual generated evidence. | I updated sentiment handling so positive, neutral, and negative categories are derived from generated responses.
8 | Sprint 2 | 2026-08-13 | 2026-08-21 | Tanusri | Start reviewing Interview Mode findings inside the same workflow. | Stop forcing the user to leave Interview Mode for analytics. | Continue keeping interview insights connected to the generated responses. | I added Insights and Scoring actions inside Interview Mode and connected them to the analytics output.
9 | Sprint 3 | 2026-08-31 | 2026-09-09 | Tanusri | Start comparing analytics counts with the actual response evidence. | Stop using fixed percentages or repeated sentiment totals. | Continue calculating metrics from the available generated responses. | I changed the analytics aggregation to calculate sentiment counts and percentages from the available responses.
10 | Sprint 3 | 2026-08-31 | 2026-09-09 | Tanusri | Start testing quality validation with different evidence sets. | Stop returning the same quality score for every scenario. | Continue basing validation on evidence coverage, theme relevance, and persona consistency. | I updated Insight Quality Validation so its score changes according to the available evidence.
11 | Sprint 3 | 2026-08-31 | 2026-09-09 | Tanusri | Start comparing findings across each research scenario. | Stop generating cross-scenario findings without supplied evidence. | Continue using scenario-level responses for insight extraction. | I updated scenario aggregation and cross-scenario insight generation to use the supplied response evidence.
12 | Sprint 3 | 2026-08-31 | 2026-09-09 | Tanusri | Start checking adoption intent against individual persona responses. | Stop showing a fixed or repeated Would Use Product percentage. | Continue presenting adoption intent as an evidence-based summary. | I updated the Would Use Product aggregation and display to reflect the generated persona evidence.
13 | Sprint 3 | 2026-09-14 | 2026-09-17 | Tanusri | Start testing the complete research workflow before generating the report. | Stop placing the Research Report action before the relevant analytics and validation output. | Continue keeping the report action connected to the completed research findings. | I positioned the Research Report action after the Insight Analytics and validation sections.
14 | Sprint 3 | 2026-09-14 | 2026-09-17 | Tanusri | Start checking PDF text flow page by page. | Stop allowing square text artifacts and unnecessary page gaps. | Continue preserving the existing charts and graphical elements. | I adjusted PDF text rendering and page flow while preserving the existing report visuals.
15 | Sprint 3 | 2026-09-14 | 2026-09-17 | Tanusri | Start checking that the final page gives a complete research conclusion. | Stop ending the report without a clear overall conclusion. | Continue keeping the conclusion consistent with the generated research evidence. | I added an overall conclusion to the final page of the Research Report.
16 | Sprint 3 | 2026-09-14 | 2026-09-17 | Tanusri | Start testing local LLM generation with larger persona counts. | Stop allowing temporary LLM failures to interrupt the complete generation flow. | Continue using structured output and retries for reliable generation. | I connected the backend to Gorq, Cerebras, Geminiand added retry/error handling for the local generation flow.